## Sheet1
Event |  |  |  | Deadlines
Capstone Timeline | Start Date | End Date | Duration | Team Formation | 2022-08-24
Project Proposal | 2022-09-11 | 2022-09-25 | 14 | Project Assignment | 2022-08-29
Project Prosal Revisions | 2022-10-05 | 2022-10-12 | 7 | Project Presentation | 2022-10-05
Conceptual Design and Planning | 2022-09-25 | 2022-10-09 | 14 | Conceptual Design and Planning Draft | 2022-10-16
Detail Design and Planning | 2022-10-09 | 2023-01-22 | 105 | Conceptual Design and Planning Review | 2022-10-19
Signoff | 2022-10-13 | 2023-01-22 | 101 | Detail Design Checkpoint 1 | 2022-11-10
Ordering | 2022-10-23 | 2023-01-29 | 98 | FMEA Video Presentation | 2022-11-17
Programming | 2022-11-16 | 2023-03-21 | 125 | Detail Design Checkpoint 2 | 2022-11-24
Build | 2022-12-01 | 2023-03-01 | 90 | Progress Report | 2022-12-11
Experimentation | 2023-03-01 | 2023-03-22 | 21 | Capstone I - Final Presentation | 2022-12-11
Documentation, Poster, Presentation | 2023-03-22 | 2023-04-28 | 37 | Detail Design Complete | 2023-01-22
|  |  |  | Ordering Complete | 2023-01-29
|  |  |  | Non-trivial fully contructed reletively functional prototype | 2023-03-01
|  |  |  | Experiementation Complete | 2023-03-22
|  |  |  | Capstone II - Final Presentation | 2023-04-28
Formulas:
Start Date = DATE(YEAR([End Date]),MONTH([End Date]),DAY([End Date])-14)
Start Date = [End Date, row above]
End Date = DATE(YEAR([Start Date]),MONTH([Start Date]),DAY([Start Date])+14)
End Date = [End Date, row above]
All date in red are +/- a week because
we do not know the exact timeline for
Capstone II