## Main
Event |  |  |  |  | Deadlines
Capstone Timeline | Start Date | End Date | Duration | Member Assignment | Team Formation | 2022-08-24
Project Proposal | 2022-09-11 | 2022-09-25 | 14 | All Team (done) | Project Assignment | 2022-08-29
Project Prosal Revisions | 2022-10-05 | 2022-10-12 | 7 | All Team (done) | Project Presentation | 2022-10-05
Conceptual Design and Planning | 2022-09-25 | 2022-10-09 | 14 | All Team | Conceptual Design and Planning Draft | 2022-10-16
Object Consumption: Detailed Design and Analytical Testing | 2022-10-31 | 2022-11-04 | 4 | Mark Beech
Vision Subsystem: Controller, Detailed Design and Analytical Testing | 2022-10-31 | 2022-11-07 | 7 | Fatima Al-Heji
Object Consumption: Signoff | 2022-11-05 | 2022-11-09 | 4 | Mark Beech
Vision Subsystem: Sensor system, Detailed Design and Analytical Testing | 2022-11-10 | 2022-11-17 | 7 | Fatima Al-Heji
Vision Subsystem: Signoff | 2022-11-18 | 2022-11-25 | 7 | Fatima Al-Heji
Object Storage: Sorting, Detail Design and Analytical Testing | 2022-11-10 | 2022-11-17 | 7 | Madison Kelly
Object Storage: Storing, Detail Design and Analytical Testing | 2022-11-17 | 2022-11-22 | 5 | Madison Kelly | Conceptual Design and Planning Review | 2022-10-19
Object Storage: Signoff | 2022-11-23 | 2022-12-09 | 16 | Madison Kelly | Detail Design Checkpoint 1 | 2022-11-10
Controller Subsystem: Detailed Design and Analytical Testing | 2022-12-09 | 2022-12-16 | 7 | Nathan Gardner | FMEA Video Presentation | 2022-11-17
Controller Subsystem: Signoff | 2022-12-16 | 2023-01-16 | 31 | Nathan Gardner | Detail Design Checkpoint 2 | 2022-11-24
Locomotion Subsystem: Motor Drivers, Detail Design and Testing | 2022-12-09 | 2022-12-16 | 7 | Luke McGill | Progress Report | 2022-12-11
Locomotion Subsystem: Motors, Detail Design and Analytical Testing | 2023-01-12 | 2023-01-19 | 7 | Luke McGill
Locomotion Subsystem: Mechanum Wheels, Detail Design and Testing | 2023-01-19 | 2023-01-22 | 3 | Luke McGill
Locomotion Subsystem: Signoff | 2023-01-22 | 2023-01-26 | 4 | Luke McGill | Capstone I - Final Presentation | 2022-12-11
Fireworks Display: Detail Design and Analytical Testing | 2023-01-12 | 2023-01-19 | 7 | Mark Beech
Fireworks Display: Signoff | 2023-01-19 | 2023-01-26 | 7 | Mark Beech
Power Subsystem: Detailed Design and Analytical Testing (LTSpice) | 2023-01-12 | 2023-01-19 | 7 | Madison Kelly
Power Subsystem: Signoff | 2023-01-20 | 2023-01-26 | 6 | Madison Kelly | Detail Design Complete | 2023-01-22
Detail Design and Planning | 2022-10-09 | 2023-01-26 | 109 | All Team | Non-trivial fully contructed reletively functional prototype | 2023-03-01
Signoff | 2022-11-05 | 2023-01-26 | 82 | All Team | Experiementation Complete | 2023-03-22
Ordering | 2022-11-05 | 2023-01-26 | 82 | All Team | Capstone II - Final Presentation | 2023-04-28
Vision Subsystem: Programming | 2023-01-27 | 2023-03-21 | 53 | Fatima Al-Heji
Controller Subsystem: Programming | 2023-01-27 | 2023-03-21 | 53 | Nathan Gardner
Build | 2023-01-12 | 2023-03-01 | 48 | All Team
Experimentation | 2023-03-01 | 2023-03-22 | 21 | All Team
Documentation, Poster, Presentation | 2023-03-22 | 2023-04-28 | 37 | All Team
DETAILED WORK BREAKDOWN
| Conceptual Design and Planning | Assignees
Documentation
| Introduction | Madison Kelly
| Formalated Problem Statement | Fatima Al-heji, Nathan Gardner
| Shall Statements | Madison Kelly, Nathan Gardner
| Ethical, Professional, and Standards Considerations | Madison Kelly, Nathan Gardner
| System Diagram | Fatima Al-heji, Nathan Gardner
| Timeline and Work Breakdown | Fatima Al-heji, Nathan Gardner
| Citations | Nathan Gardner
System Diagram Design
| LucidChart Diagrams | Mark Beech, Luke Mcgill, Nathan Gardner, Madison Kelly
| Power System | Madison Kelly
| Controller | Nathan Gardner
| Locomotion | Luke Mcgill
| Vision System | Nathan Gardner
| Object Manipulation | Mark Beech, Madison Kelly
Miscellaneous
| Gantt Chart | Nathan Gardner, Madison Kelly
| Detail Design and Planning | Assignees
Subsystems Design
| Chassis | Mechanical Team
| Microcontroller System | Nathan Gardner
| Vision System | Fatima Al-heji, Nathan Gardner, Luke Mcgill
| Consumption of Objects | Mechanical Team, Mark Beech, Madison Kelly
| Object Storage | Mechanical Team, Mark Beech
| Object Delivery | Mechanical Team, Mark Beech, Madison Kelly
| Locomotion | Mechanical Team, Luke McGill
| Fireworks Display | Fatima Al-heji
| Animal Feeding | Mechanical Team, Fatima Al-heji, Nathan Gardner, Luke Mcgill
| Power | Madison Kelly, Mark Beech
Miscellaneous
| Gantt Chart | Nathan Gardner, Madison Kelly
Formulas:
Start Date = DATE(YEAR([End Date]),MONTH([End Date]),DAY([End Date])-14)
End Date = DATE(YEAR([Start Date]),MONTH([Start Date]),DAY([Start Date])+14)
End Date = [End Date, row above]
All date in red are +/- a week because
we do not know the exact timeline for
Capstone II

## DD-Object Manipulation
\