## Main
Event |  |  |  |  | Deadlines
Capstone Timeline | Start Date | End Date | Duration | Member Assignment | Team Formation | 2022-08-24
Project Proposal | 2022-09-11 | 2022-09-25 | 14 | Complete | Project Assignment | 2022-08-29
Project Prosal Revisions | 2022-10-05 | 2022-10-12 | 7 | Complete | Project Presentation | 2022-10-05
Conceptual Design and Planning | 2022-09-25 | 2022-10-09 | 14 | Enitire Team | Conceptual Design and Planning Draft | 2022-10-16
Locomotion Subsystem: motor driver | 2022-10-26 | 2022-10-04 |  |  | Conceptual Design and Planning Review | 2022-10-19
Locomotion Subsystem: motor | 2022-10-26 | 2022-10-04 |  |  | Detail Design Checkpoint 1 | 2022-11-10
Locomotion Subsystem: wheels | 2022-10-26 | 2022-10-04 |  |  | FMEA Video Presentation | 2022-11-17
Controller Subsystem: |  |  |  |  | Detail Design Checkpoint 2 | 2022-11-24
Power Subsystem: |  |  |  |  | Progress Report | 2022-12-11
[5 empty] | Capstone I - Final Presentation | 2022-12-11
[5 empty] | Detail Design Complete | 2023-01-22
Vision Subsystem: |  |  |  |  | Ordering Complete | 2023-01-29
Detail Design and Planning | 2022-10-09 | 2023-01-22 | 105 |  | Non-trivial fully contructed reletively functional prototype | 2023-03-01
Signoff | 2022-10-13 | 2023-01-22 | 101 |  | Experiementation Complete | 2023-03-22
Ordering | 2022-10-23 | 2023-01-29 | 98 |  | Capstone II - Final Presentation | 2023-04-28
Programming | 2022-11-16 | 2023-03-21 | 125
Build | 2022-12-01 | 2023-03-01 | 90
Experimentation | 2023-03-01 | 2023-03-22 | 21
Documentation, Poster, Presentation | 2023-03-22 | 2023-04-28 | 37
DETAILED WORK BREAKDOWN
| Conceptual Design and Planning | Assignees
Documentation
| Introduction | Madison Kelly
| Formalated Problem Statement | Fatima Al-heji, Nathan Gardner
| Shall Statements | Madison Kelly
| Ethical, Professional, and Standards Considerations | Madison Kelly
| System Diagram | Fatima Al-heji, Nathan Gardner
| Timeline and Work Breakdown | Fatima Al-heji, Nathan Gardner
| Citations | Nathan Gardner
System Diagram Design
| LucidChart Diagrams | Mark Beech, Luke Mcgill, Nathan Gardner
| Power System | Luke Mcgill
| Controller | Nathan Gardner
| Locomotion | Luke Mcgill
| Vision System | Nathan Gardner
| Object Manipulation | Fatima Al-heji, Nathan Gardner
| Microbot | Mark Beech
Miscellaneous
| Gantt Chart | Nathan Gardner
| Detail Design and Planning | Assignees
Subsystems Design
| Chassis | Mechanical Team
| Location Determination and Tracking | Fatima Al-heji, Nathan Gardner, Luke Mcgill
| Object Detection | Fatima Al-heji, Nathan Gardner, Mark Beech
| Object Manipulation | Mechanical Team, Fatima Al-heji, Nathan Gardner, Luke Mcgill
| Locomotion | Mechanical Team
| Fireworks Display | Fatima Al-heji
| Animal Feeding | Mechanical Team, Fatima Al-heji, Nathan Gardner, Luke Mcgill
| Power | Madison Kelly, Mark Beech
Miscellaneous
| Gantt Chart | Nathan Gardner
Formulas:
Start Date = DATE(YEAR([End Date]),MONTH([End Date]),DAY([End Date])-14)
Start Date = DATE(YEAR([Start Date, row above]),MONTH([Start Date, row above]),DAY([Start Date, row above])+4)
End Date = DATE(YEAR([Start Date]),MONTH([Start Date]),DAY([Start Date])+14)
End Date = [End Date, row above]
All date in red are +/- a week because
we do not know the exact timeline for
Capstone II

## DD-Object Manipulation
\