## Sheet1
Event
Capstone I (with specific dates) | Set Date
Team Formation | 2022-08-24
Project Assignment | 2022-08-29
Project Proposal | 2022-09-25
Project Presentation | 2022-10-05
Project Prosal Revisions | 2022-10-12
Conceptual Design and Planning Draft | 2022-10-16
Conceptual Design and Planning Review | 2022-10-19
Conceptual Design and Planning | 2022-10-30
Detail Design Checkpoint 1 | 2022-11-10
FMEA Video Presentation | 2022-11-17
Detail Design Checkpoint 2 | 2022-11-24
Progress Report | 2022-12-11
Final Presentation | 2022-12-11
Capstone II (with rough date range based on previous year) | Date Begin | Date End
Detail Design Complete | 2022-01-15 | 2022-01-22
Ordering Complete | 2022-01-22 | 2022-01-29
Non-trivial fully contructed reletively functional prototype | 2022-02-22 | 2022-03-01
Experiementation Complete | 2022-03-15 | 2022-03-22
Final Presentation Practice | 2022-04-05 | 2022-04-12
Improvements Complete | 2022-04-11 | 2022-04-18
Poster Complete | 2022-04-14 | 2022-04-21
Final Documentation Complete | 2022-04-18 | 2022-04-25
Final Presentation | 2022-04-19 | 2022-04-26